## Sheet1
CAPSTONE PROJECT 1 TIMELINE
Proposal | Draft Proposal (One-Page Proposal) | 2nd Week of March
| Title Proposal (Chapters 1 to 3 – initial) | Last Week of March
| Project Proposal (Chapters 1 to 3 – final) | Last Week of April
System | Project Requirements (Systems Analysis & Design) | Last Week of April
| Prototype Design (with partial modules) | Last Week of April
Panel Defense | Project Proposal (Complete Requirements) | Start: Last Week of April End: 2nd Week of May
*NO EXTENSION for the Proposal Defense
Schedule of Systems Analysis and Design (SAD)* Requirements
1 | Software Development Methodology | 2023-03-06
2 | Gantt Chart (Project Activities) | 2023-03-06
3 | Interview Guide Questions / Survey Questions | 2023-03-13
4 | Activity Diagram - Existing System | 2023-03-20
5 | Compilation of I/O Forms (Forms and Reports) - Existing System | 2023-03-20
6 | Context-Flow Diagram (DFD) - Proposed System | 2023-03-27
7 | Use-Case Model - Proposed System | 2023-03-27
8 | Data Flow Diagram (Diagram 0 & Child Diagrams) - Proposed System | 2023-03-27
9 | Sequence Diagram - (Proposed System) | 2023-04-03
10 | I/O Layout Design (Screen Designs) - Proposed System | 2023-04-10
11 | Database Designs (ERD and Class Diagram) - Proposed System | 2023-04-17
12 | Data Dictionary (Complete) - Proposed System | 2023-04-24
* NOTE: Not all of you will be performing SAD. SAD is used to analyze and design information systems. (Exemption: Game Development, Machine Learning, etc.)
* SAD Requirements will depend on the advice of your CONTENT ADVISER & PROGRAMMING ADVISER